COVID-19 Impact on Research Development & Innovation Activities

- In the context of the current COVID-19 pandemic, UHB research activities will need to be limited in order to:

- Reduce or minimise visits to the Trust sites by patients, research participants and other research-related visitors (including study monitors).

- Reduce the activities of non-essential research staff and research-support staff.

- Reduce the risk of placing participants at greater risk of COVID-19 infection and/or of more severe illness, if infected.

- In the event that COVID-19 places extreme pressure on NHS services, UHB research staff, research support staff and facilities will be redeployed to support clinical services in agreement with the Director and/or Deputy Director R,D & I.

- UHB RD&I are currently in the process of reviewing: a) all research activities which are currently actively recruiting patients: b) all non-directly patient facing research activities;  c) all research activities which are in set-up phase with previously agreed start dates: d) all research activities which are at pre-set-up/SIV stage. Once this process is complete, prioritisation of research activities will take place with the support of Principal Investigators (PIs)/Chief Investigators (CIs) and Sponsors. Where prioritisation requirement relates to research infrastructure (for example: NIHR Clinical Research Facilities: NIHR BRC: IUK Midlands & Wales Advanced Therapy Treatment Centre: HDR-UK hubs) the appropriate Director will be involved. A phased approach to management of research activities is described below. This will be informed by UHB-mandated actions and the availability of research and research support staff.

- The decision to proceed with each Stage will be made by the Chief Innovation Officer, Director of RD&I and Clinical Director of RD&I in consultation with the Chief Medical Officer and Chief Operating Officer, or their nominated deputies.

- UHB RD&I will be responsible for communicating decisions to Principal Investigators (PIs); Chief Investigators (CIs); Research Infrastructure Directors and research support staff, and following up as required. UHB RD&I will work closely with University of Birmingham colleagues, in order to ensure effective communication and actions. PIs/CIs will be expected to communicate directly with clinical trial study sponsors, and keep the RD&I office appraised of any non-alignment of sponsor and UHB requirements.

- The current Stage will be reviewed and updated as required on at least a twice-weekly basis until such time as specific actions are no longer required.

- Research studies which are directly related to COVID-19 will be prioritised for delivery.

Stages in Progression for Management of UHB Research Development & Innovation Activities

| Stage 1: Preparation | Stage 2: Limit research activities | Stage 3: Essential research activity only |
| --- | --- | --- |
| Review all active clinical trials and those in set-up phases to identify trials which may require special consideration, i.e. those: which may put participants at increased risk of COVID-19 infection and/or of more severe illness if infected - where clinical care is research protocol dependent (for example novel chemotherapy regimes) - related directly to COVID-19 Liaise with CI/PIs and Sponsors to develop and agree management plans for active clinical trials Review all CTIMP medical products associated with active clinical trials and develop mitigation plans for continuity of supply and dispensing in collaboration with Sponsors Review all non-directly patient facing research activities to identify opportunities for “video” first / remote working Review as a priority all PI/CI’s trial portfolio’s in specialities which are likely to be impacted by staff redeployment to clinical areas (eg ITU, Respiratory) Develop plans for suspension/ delay of on-sites activities (for example: medical device simulation testing/userability studies | Suspend set-up of new studies with the exception of those directly related to COVID-19 Suspend recruitment to all studies with the exception of those where clinical care is research protocol dependant Suspend studies which may put participants at increased risk of COVID-19 infection and/or of more severe illness if infected Continue study visits for participants already recruited to other studies, minimising their visits to UHB sites, e.g. by carrying out remote follow-up where possible. Implement “video” first/remote working as appropriate and in agreement with direct line managers Implement plans for suspension/delay of research activities for non-directly patient facing research | Suspend all activities for research activities with the exception of those clinical trials - where clinical care is research protocol dependent - related directly to COVID-19 |